## Timeline
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Work Packages
Start | End | Duration | Label | Vert. Position | Vert. Line
2023-09-20 | 2023-10-04 | 15 | Literature research Sep 20 - Oct 4 | -20 | -20
2023-10-05 | 2023-10-14 | 10 | Pose estimation simulation Oct 5 - Oct 14 | -35 | -15
2023-10-15 | 2023-10-19 | 5 | Qtrobot environment learning Oct 15 - Oct 19 | -50 | -15
2023-10-20 | 2023-11-08 | 20 | Path planning framework development Oct 20 - Nov 8 | -65 | -65
2023-11-09 | 2023-11-28 | 20 | Trajectory learning from demonstration Nov 9 - Nov 28 | -80 | -80
2023-11-29 | 2023-12-03 | 5 | Evaluation with QT Nov 29 - Dec 3 | -95 | -15
2023-12-04 | 2023-12-08 | 5 | Simulation with NAO Dec 4 - Dec 8 | -20 | -20
2023-12-09 | 2023-12-18 | 10 | NAO environment learning Dec 9 - Dec 18 | -35 | -35
2023-12-19 | 2024-01-02 | 15 | Framework implementation on NAO Dec 19 - Jan 2 | -50 | -50
2024-01-03 | 2024-01-07 | 5 | Evaluation with NAO Jan 3 - Jan 7 | -65 | -65
2024-01-08 | 2024-01-12 | 5 | Simulation with Freddy Jan 8 - Jan 12 | -80 | -80
2024-01-13 | 2024-01-17 | 5 | Freddy environment learning Jan 13 - Jan 17 | -95 | -95
2024-01-18 | 2024-02-01 | 15 | Framework implementation on Freddy Jan 18 - Feb 1 | -20 | -20
2024-02-02 | 2024-02-16 | 15 | Evaluation with Freddy Feb 2 - Feb 16 | -35 | -35
2024-02-17 | 2024-02-21 | 5 | Voice command integration for QT Feb 17 - Feb 21 | -50 | -50
2024-02-22 | 2024-03-19 | 27 | Report Feb 22 - Mar 19 | -65 | -65
2024-03-20 | 2024-03-20 | 1 | Report submission Mar 20 | -80 | -80
Milestones
Date |  |  | Label | Position
2023-09-20 |  |  | Start, Sep 20 | 5
2023-10-14 |  |  | Simulation of skeleton imitation with all robots | 13
2023-11-29 |  |  | Framework - Implementation and evaluation on Qtrobot | 15
2024-01-08 |  |  | Implementation and evaluation on NAO | 15
2024-02-17 |  |  | Implementation and evaluation Freddy | 15
2024-03-20 |  |  | Master Thesis Submission, Mar 20 | 5
Formulas:
End = [Start]+[Duration]-1
Start = [End, row above]+1

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.