## Timeline
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Work Packages
Start | End | Duration | Label | Vert. Position | Vert. Line
2023-08-01 | 2023-08-15 | 15 | Literature research Aug 1 - Aug 15 | -20 | -20 | #VALUE!
2023-08-16 | 2023-08-25 | 10 | Pose estimation simulation Aug 16 - Aug 25 | -35 | -15
2023-08-26 | 2023-08-30 | 5 | Qtrobot environment learning Aug 26 - Aug 30 | -50 | -15
2023-08-31 | 2023-09-19 | 20 | Path planning framework development Aug 31 - Sep 19 | -65 | -65
2023-09-20 | 2023-10-09 | 20 | Trajectory learning from demonstration Sep 20 - Oct 9 | -80 | -80
2023-10-10 | 2023-10-14 | 5 | Evaluation with QT Oct 10 - Oct 14 | -95 | -15
2023-10-15 | 2023-10-19 | 5 | Simulation with NAO Oct 15 - Oct 19 | -20 | -20
2023-10-20 | 2023-10-29 | 10 | NAO environment learning Oct 20 - Oct 29 | -35 | -35
2023-10-30 | 2023-11-13 | 15 | Framework implementation on NAO Oct 30 - Nov 13 | -50 | -50
2023-11-14 | 2023-11-18 | 5 | Evaluation with NAO Nov 14 - Nov 18 | -65 | -65
2023-11-19 | 2023-11-23 | 5 | Simulation with Freddy Nov 19 - Nov 23 | -80 | -80
2023-11-24 | 2023-11-28 | 5 | Freddy environment learning Nov 24 - Nov 28 | -95 | -95
2023-11-29 | 2023-12-13 | 15 | Framework implementation on Freddy Nov 29 - Dec 13 | -20 | -20
2023-12-14 | 2023-12-28 | 15 | Evaluation with Freddy Dec 14 - Dec 28 | -35 | -35
2023-12-29 | 2024-01-02 | 5 | Voice command integration for QT Dec 29 - Jan 2 | -50 | -50
2024-01-03 | 2024-01-31 | 29 | Report Jan 3 - Jan 31 | -65 | -65
2024-02-01 | 2024-02-01 | 1 | Report submission Feb 1 | -80 | -80
Milestones
Date |  |  | Label | Position
2023-08-01 |  |  | Start, Aug 1 | 5
2023-08-25 |  |  | Simulation of skeleton imitation with all robots | 13
2023-10-10 |  |  | Framework - Implementation and evaluation on Qtrobot | 15
2023-11-19 |  |  | Implementation and evaluation on NAO | 15
2023-12-29 |  |  | Implementation and evaluation Freddy | 15
2024-02-01 |  |  | Master Thesis Submission, Feb 1 | 5
Formulas:
End = [Start]+[Duration]-1
Start = [End, row above]+1

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.